## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Status(Open/Closed) | Remarks
1 | sakshi salgare | 10-02-2026 | Uploaded documents not refreshing after restart | Sprint 1 | Self | Logical | 12-02-2026 | Closed | Data refresh issue resolved
2 | sakshi salgare | 14-02-2026 | Chat response delay due to slow embedding generation | Sprint 1 | Self | Standards | 16-02-2026 | Closed | Improved response speed
3 | sakshi salgare | 20-02-2026 | Incorrect answers due to poor chunk retrieval | Sprint 2 | Self | Logical | 23-02-2026 | Closed | Retrieval accuracy improved
4 | sakshi salgare | 25-02-2026 | Duplicate documents appearing after multiple uploads | Sprint 2 | Self | Logical | 27-02-2026 | Closed | Citation issue resolved
5 | sakshi salgare | 05-03-2026 | Missing source citations in some responses | Sprint 3 | Self | Standards | 08-03-2026 | Closed | Duplicate issue fixed
6 | sakshi salgare | 10-03-2026 | UI not updating chat history properly | Sprint 3 | Self | Standards | 12-03-2026 | Closed | Large file support added
7 | sakshi salgare | 18-03-2026 | File upload fails for large PDFs | Sprint 4 | Self | Logical | 20-03-2026 | Closed | Config issue resolved
8 | sakshi salgare | 25-03-2026 | Application crash due to missing environment variables | Sprint 4 | Self | Standards | 27-03-2026 | Closed | Chat UI improved

## Sheet2
Logical
User Interface
Maintainability
Standards
Others